## Slide 1: What’s Top-Down appoach and how to apply it?

## Slide 2: 01 What is a Top-down Approach?

## Slide 3: What is a Top-down Approach?
A top-down approach is about breaking down a system into the subsystems that make it up. The process can be repeated to break down subsystems into low-level elements like classes and method

## Slide 4: 02 How to apply the Top-down Approach?

## Slide 5: How to apply the Top-down Approach? 1 2 3
Define the Problem or Goal
Create a High-Level Overview
Identify Subsystems or Modules
4
5
Detail Each Subsystem
Repeat the Process

## Slide 6: How to apply the Top-down Approach?
Assign Tasks
Develop Each Component
Integration and Testing
Refinement
Completion and Evaluation
6
7
8
9
10

## Slide 7: 03 Benefits and challenges of the Top-Down strategy

## Slide 8: Benefits of Top-Down strategy
Rigid and structured system.
Employees are clear about the tasks they need to focus on.
Risk mitigation.
Management staff with authority.
Ease of problem identifications.

## Slide 9: Rigid and structured system
A top-down management approach will help provide clear and well-structured processes for correct operations

## Slide 10: Employees are clear about the tasks they need to focus on
All employees will have clearly defined responsibilities within the organization, which will help them focus solely on doing their jobs properly.

## Slide 11: Risk mitigation
The top-down approach minimizes the risk of assigning strategic responsibilities to employees with incompatible profiles or those prone to discord and anarchy, ensuring alignment with their designated roles and functions.

## Slide 12: Management staff with authority
The decision-making in organizations that adopt a Top-Down management approach is highly centralized in their highest authority, who decides both the strategic planning and the way in which this strategy will be executed.

## Slide 13: Ease of problem identifications
By having all teams with well-defined tasks, it is easier to identify the root cause of problems and bottlenecks in the organization’s business processes

## Slide 14: Top-Down approach challenges
Mission Disconnect
Stifled Creativity and Proactivity
Limited Adaptability
Potential for Dictatorship.

## Slide 15: Mission Disconnect
Employees may lose sight of the organization's mission and vision.
Long-term disconnection from the company's purpose.

## Slide 16: Stifled Creativity and Proactivity
well-defined responsibilities, lack proactivity in addressing management problems beyond their direct concerns.
Teams may avoid proposing solutions outside established standards.

## Slide 17: Low capacity to respond to new challenges
Struggles in responding to new challenges.
Rigid approach hampers adaptation to strategy changes or complex issues.

## Slide 18: Potential for Dictatorship
There is a risk of displeasing employees seeking autonomy or being excluded from decisions.
if poorly executed and without proper communication, can lead to a high turnover rate in companies.

## Slide 19
Their production systems must comply with quality control measures.
Or areas with a lot of regulations and policies (Regulations at the international level, Cybersecurity, Compliance, etc.).
This Top-Down approach is necessary to minimize any margin of error.
Which areas are suitable for a top-down approach?

## Slide 20: THANKS FOR WATCHING